## Slide 1: WoT IG and WG Administration
WoT F2F Meeting
Dusseldorf, Germany, July, 2017

## Slide 2: Upcoming F2F Meetings

## Slide 3: F2F Meeting November 2017: Burlingame, CA, USA
At TPAC 2017
6–10 November 2017 – F2F on Mon+Tue
4 months to work
Calendars
  IETF: 11-16, Singapore
  OCF: Nov 6-10, Singapore
Todos
  PlugFest: Organize hacker space for Saturday and Sunday (4-5)  Michael K.
  WoT Demo: Request full-day room or at least 3 hours on Wednesday

## Slide 4: F2F Meeting Spring 2018: ~End of Feb / Mar in Asia
Co-location with security conference
  Might be difficult  separate activity
  https://www.internetsociety.org/events/ndss-symposium/ndss-symposium-2018 (San Diego, 18-21 February)
  https://www.ieee-security.org/TC/SP2018/ (San Jose, 21-23 May)
Look at calendars
  IETF: London, UK, 18–23 March 2018
  OCF:
  oneM2M: Asia, 21.. May 2018
Todos
  Organize academic conference workshop (with T2TRG)
  Discuss in chairs call

## Slide 5: F2F Meeting Summer 2018: ~End of June in Americas
Look at calendars
  IETF: July 22-27 2018 (San Francisco)
  OCF?
  oneM2M?
x months to work
Todos
  Check alternatives in Korea and Taiwan
  Consider visas

## Slide 6: F2F Meeting October 2018: Lyon, France
At TPAC 2018
22–26 Oct 2018
Look at calendars
  IETF: 4-9 Nov 2018 (location tbd)
  OCF?
  oneM2M?
x months to work
Todos

## Slide 7: Next Steps

## Slide 8: WG Roadmap
2017-02 (Santa Clara F2F)
  Create GitHub repos
2017-05 (Osaka F2F)
  Graphical and RDF model of TD
  Editor’s Drafts
  RC for WoT Architecture First Public Working Draft (FPWD)
  Start security review for WoT Architecture
2017-07 (Düsseldof F2F)
  Finish security review for WoT Arch. with Internet Drafts (“security concepts”) for internal security review and IETF outreach
  Draft for test suite (Servient emulator with automatic checks)
  Release First Public Working Draft (FPWD) of WoT Architecture
2017-11 (TPAC 2017, Burlingame, CA, USA)
  RCs for First Public Working Drafts
  RC Implementations and Test Suite
  Start external security review
2018-03 (London? F2F)
  Finish external security review
  Release First Public Working Drafts (FPWDs)
2018-05 (F2F at sec conf, Santa Clara?)
  Aggressive testing / adverse security testing?
2018-07 (China? F2F)
2018-10
  RCs for Candidate Recommendations
  Start security review
2018-11 (TPAC 2018, Asia?)
  Finish security review
  Start release process
2018-12 (end of current charter)
  Release Candidate Recommendations (CRs)